## project
ID | Project name | Project goal | Source | Launch date | Funding status jan 2022 | Link | Contact | Location | Country | Category | Backers | Goal EUR | Total amount funded EUR | % Funded | Estimated delivery | Planned duration | Delivery completed | Slippage(days) | Slippage (perc) | Delivery status | Optional: Details on problems | Team size | Planning steps after kickstarter launch | Words in risk section | Earlier kickstarter project | Retail price (€) | Retail price-local currency | Comments
1001 | AER | Throwing go pro device | funded-2yrs-eveleens-oct2020 | 2016-10-04 | Funded | https://www.kickstarter.com/projects/aervideo/aer-throw-your-gopro | info@aervideo.com | Enschede, Netherlands | Netherlands | Technology | 1947 | 70000 | 123602 | 176.6% | 2017-01-01 | 89 | 2017-10-10 | 282 | 316.9% | 6-24 month delay |  | 4 | 3 | 88 | 0 | 60
1002 | Alhambra Designer's edition | A revamped new game | funded-2yrs-eveleens-oct2020 | 2018-04-25 | Funded | https://www.kickstarter.com/projects/1082720051/alhambra-designers-edition |  | Cologne, Germany | Germany | Games | 2212 | 10000 | 283533 | 2835% | 2019-03-01 | 310 | 2020-01-16 | 321 | 103.5% | 6-24 month delay |  | 6 | 0 | 132 | 14 | 200
1003 | AlpinerX | Smartwatch | funded-2yrs-eveleens-oct2020 | 2018-03-22 | Funded | https://www.kickstarter.com/projects/536565656/alpinerx-the-most-beautiful-outdoors-smartwatch?ref=producthype | smartwatchsupport@alpina-watches.com | Geneva, Switserland | Switzerland | Design | 2795 | 47938 | 1505145 | 3140% | 2018-06-30 | 100 | 2018-10-01 | 93 | 93% | Delivered on time |  | 12 | 1 | 235 | 0 | 370
1004 | Aurga | Smart DSLR Assistent | funded-2yrs-eveleens-oct2020 | 2018-03-07 | Funded | https://www.kickstarter.com/projects/1126926170/aurga-smart-camera-assistant-and-personal-cloud-st | info@aurgadslr.com | Los Angeles | US | Technology | 941 | 16802 | 95474 | 568.2% | 2018-05-01 | 55 | 2018-06-26 | 56 | 101.8% | Delivered on time |  | 5 | 1 | 117 | 0 | 114.1507 | 130
1005 | Bee scanning | Scanner to save investation in bee colonies | funded-2yrs-eveleens-oct2020 | 2017-05-01 | Funded | https://www.kickstarter.com/projects/1418874888/beescanning | fribi@mac.com | Stockholm, Sweden | Sweden | Technology | 317 | 4867 | 10763 | 221.1% | 2017-12-31 | 244 | 2018-06-06 | 157 | 64.34% | Delivered on time |  | 8 | 6 | 162 | 0 | 0
1006 | Circa | Smart alarm app that helps you sleep | funded-2yrs-eveleens-oct2020 | 2017-11-09 | Funded | https://www.kickstarter.com/projects/2071439898/circa-the-stand-alone-smart-alarm-that-helps-you-s?ref=discovery_category_newest |  | Rotterdam, Netherlands | Netherlands | Design | 474 | 100000 | 117056 | 117.1% | 2018-06-01 | 204 | Not delivered | -1 | -0.4902% | Not delivered | Nov 8 2019: It has been quiet from our side for some time. As we informed you before, we had to put the project on hold due to high display prices, technology issues, and financial problems. We have made progress on some of the issues but we don’t have a final solution yet. | 8 | 6 | 202 | 0 | 225
1007 | GOSPACE | Expandable 5G wireless storage | funded-2yrs-eveleens-oct2020 | 2018-01-30 | Funded | https://www.kickstarter.com/projects/722274067/gospace-expandable-5g-wireless-storage-and-streami |  | Santa Monica | US | Technology | 2332 | 16802 | 178716 | 1064% | 2018-05-01 | 91 | Not delivered | -1 | -1.099% | Not delivered | It’s seems they have gone, disappeared, and it doesn’t look like we’re going to get anything no updates from so long. I do want full refund too! | 4 | 3 | 97 | 0 | 87.8082 | 100
1008 | Halzae | Videogame from students | funded-2yrs-eveleens-oct2020 | 2018-11-13 | Funded | https://www.kickstarter.com/projects/362994230/halzae-heroes-of-divinity-from-students-to-indiede?ref=discovery_category_newest |  | Nimes, France | France | Games | 84 | 10000 | 10239 | 102.4% | 2018-12-01 | 18 | Not delivered | -1 | -5.556% | Not delivered | Website is not available: https://www.halzae.com/home | 13 | 5 | 97 | 0 | 0
1009 | HEY | Wearable bracelet sending your touch | funded-2yrs-eveleens-oct2020 | 2017-02-13 | Funded | https://www.kickstarter.com/projects/1596731227/hey-a-revolutionary-bracelet-that-sends-touch-over?ref=discovery_category | info@feelhey.com | Utrecht, Netherlands | Netherlands | Technology | 1553 | 125000 | 148839 | 119.1% | 2017-08-01 | 169 | 2018-10-08 | 433 | 256.2% | 6-24 month delay | Note:Got my bracelets. They are massive and look more like house arrest bracelets than what was in the promotions. After using them I also realized they are loud when administering the "touch". Overall really disappointed in the product. | 5 | 6 | 179 | 0 | 120
1010 | Kira | Mechanical keyboard | funded-2yrs-eveleens-oct2020 | 2018-03-27 | Funded | https://www.kickstarter.com/projects/lekashman/kira-mechanical-keyboard | business@input.club | San Jose | US | Technology | 1682 | 42030 | 340707 | 810.6% | 2018-10-01 | 188 | 2019-02-08 | 130 | 69.15% | Delivered on time | Communications were our most dire failure in the fulfillment process. This was, in part, caused by the automation failures. For example, Kono’s customer support manager prepared most of the raw data for Kono’s manual order upload process. He also entered more than 1,000 tracking numbers over the last two weeks, which required cross-referencing and numerous mouse clicks per entry. More work than usual and much less time to accomplish it led to less overall community interaction. | Unknown | 0 | 131 | 3 | 157.1767 | 179
1011 | LeveTop | Autonomous Folding Drone | funded-2yrs-eveleens-oct2020 | 2018-03-13 | Funded | https://www.kickstarter.com/projects/1727015699/levetop-the-autonomous-folding-drone | info@levetop.com | Los Angeles | US | Technology | 1208 | 21006 | 175614 | 836% | 2018-06-01 | 80 | 2019-01-01 | 214 | 267.5% | 6-24 month delay | Note: updates not public. Several backers are disappointed:Changed phones and find no way to get my new phone connected. Appears this project is now defunct and unable to support their customers. Never really worked all that well, and not even sufficiently for a paper weight... | 8 | 3 | 58 | 0 | 306.4506 | 349
1012 | LeviZen | Water levitator | funded-2yrs-eveleens-oct2020 | 2018-02-28 | Funded | https://www.kickstarter.com/projects/1348567444/levizen-levitate-water-and-feel-zero-gravity?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Blog |  | Burbank | US | Technology | 882 | 12604 | 153715 | 1220% | 2018-07-01 | 123 | Not delivered | -1 | -0.813% | Not delivered | Update 16 feb 2019: There is a clear reason as to why we encountered difficulties in fulfilling our previous project and why currently we are experiencing delays with LeviZen. The reason is that, established companies with big budgets and capabilities don’t dare to think of making complicated products that require the utmost precision in manufacturing for just a very small group of customers and losing a lot of money. | Unknown | 0 | 70 | 2 | 350.3547 | 399
1013 | MasterSous | 8 in 1 smart cooker | funded-2yrs-eveleens-oct2020 | 2018-10-23 | Funded | https://www.kickstarter.com/projects/mastersous/mastersous-the-8-in-1-smart-cooker?ref=phtech.go2.fund&utm_medium=referral&utm_source=phtech.go2.fund | sletter@producthype.co | North Carolina | US | Technology | 798 | 33613 | 179791 | 534.9% | 2019-10-01 | 343 | Not delivered | -1 | -0.2915% | Not delivered | Update feb 2020: We had been hoping to give a more specific date for the shipping of the MasterSous as spring 2020 approached. Unfortunately, however, the outbreak of the Coronavirus has momentarily paused production, as factories are short-staffed due to health precautions. We are working hard to get things back up and running as soon as possible and will provide more updates as they are available. | Unknown | 1 | 97 | 0 | 351.2328 | 400
1014 | Mayu | Keep you water healthy | funded-2yrs-eveleens-oct2020 | 2018-10-23 | Funded | https://www.kickstarter.com/projects/mayuwater/mayu-keep-your-water-healthy-with-a-natural-swirli?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=c23c0c8e | contact@mayuwater.com | Israel | Israel | Design | 3986 | 25204 | 433384 | 1720% | 2019-05-01 | 190 | Not delivered | -1 | -0.5263% | Not delivered | Severalbackers reportthat they have not received it: "I’m living in the Netherlands and still have not received my Mayu’s. What’s the matter?" "I live in Sweden and have not yet received any Mayu shipment." "Hello, the carafe arrived three days ago, and was really impressive, but unfortunately it seems to have already stopped working." | 8 | 3 | 72 | 0 | 148.3959 | 169
1015 | Moment | Filmmaker tool | funded-2yrs-eveleens-oct2020 | 2018-03-27 | Funded | https://www.kickstarter.com/projects/moment/the-future-of-mobile-filmmaking-anamorphic-battery?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Blog | hello@shopmoment.com | Seattle | US | Design | 10533 | 42030 | 1334189 | 3174% | 2018-06-01 | 66 | 2019-01-21 | 234 | 354.5% | 6-24 month delay | Being late. It’s always bad. It then leads to a cascade list of other bad trade offs, missed vacations, and negativity. Our own conservative estimates on the schedule turned out to be worse than anything we projected. | 19 | 8 | 179 | 6 | 158.0548 | 180
1016 | Mycroft Mark II | Open voice assistent | funded-2yrs-eveleens-oct2020 | 2018-01-25 | Funded | https://www.kickstarter.com/projects/aiforeveryone/mycroft-mark-ii-the-open-voice-assistant | founders@mycroft.ai | Kansas City | US | Technology | 2245 | 42030 | 331588 | 788.9% | 2018-03-01 | 35 | Not delivered | -1 | -2.857% | Not delivered | Note: updates are still being made, apparently project is still ongoinng | 17 | 3 | 434 | 2 | 113.2726 | 129
1017 | NATEDE | Smart purifier | funded-2yrs-eveleens-oct2020 | 2018-04-17 | Funded | https://www.kickstarter.com/projects/vitesy/natede-the-most-amazing-smart-natural-air-purifier | hello@vitesy.com | San Fransisco | US | Technology | 3821 | 50000 | 765265 | 1531% | 2018-12-01 | 228 | 2020-09-30 | 669 | 293.4% | 6-24 month delay |  | 19 | 5 | 65 | 3 | 300 | 30
1018 | Nebula Capsule II | Android TV Pocket cinema | funded-2yrs-eveleens-oct2020 | 2018-10-26 | Funded | https://www.kickstarter.com/projects/nbl/nebula-capsule-ii-worlds-first-android-tvtm-pocket | support@seenebula.com | Seattle | US | Technology | 4018 | 42030 | 1410156 | 3355% | 2019-05-01 | 187 | 2019-05-01 | 0 | 0% | Delivered on time |  | Unknown | 4 | 82 | 2 | 525.9711 | 599
1019 | OFF GRID | Hacking game | funded-2yrs-eveleens-oct2020 | 2018-10-09 | Funded | https://www.kickstarter.com/projects/richmetson/off-grid-data-is-your-most-powerful-weapon?ref=discovery_category |  | Essex, UK | UK | Games | 572 | 20000 | 25252 | 126.3% | 2019-12-01 | 418 | Not delivered | -1 | -0.2392% | Not delivered | During the Kickstarter campaign, we promised delivery of the game by December 2019. This is possible, but we believe OFF GRID would be better served by delaying its release into 2020. | 4 | 0 | 205 | 0 | 21.5302 | 18
1020 | Ohnana | Festival tent | funded-2yrs-eveleens-oct2020 | 2017-06-22 | Funded | https://www.kickstarter.com/projects/ohnana/ohnana-the-coolest-tent-for-festival-lovers | hello@ohnanatents.com | Amsterdam, Netherlands | Netherlands | Design | 396 | 25000 | 38075 | 152.3% | 2017-07-01 | 9 | 2017-08-01 | 31 | 344.4% | Delivered on time |  | 7 | 1 | 101 | 0 | 119.612 | 100
1021 | Phoenix springs | Adventure game | funded-2yrs-eveleens-oct2020 | 2017-08-01 | Funded | https://www.kickstarter.com/projects/20171617/phoenix-springs-a-neo-noir-mystery-adventure-game?ref=discovery_category |  | London, UK | UK | Games | 240 | 9000 | 10625 | 118.1% | 2018-03-01 | 212 | Not delivered | -1 | -0.4717% | Not delivered | Update 2020: I'd say it's about 75% done. Thanks again so much for your patience - I really screwed up the Kickstarter timing :/ | 3 | 4 | 112 | 0 | 15
1022 | PITTA | 4K Selfie drone | funded-2yrs-eveleens-oct2020 | 2017-12-20 | Funded | https://www.kickstarter.com/projects/1627662609/pitta-transformative-autonomous-4k-selfie-drone?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Post |  | Los Angeles | US | Technology | 1706 | 42030 | 467843 | 1113% | 2018-04-01 | 102 | Not delivered | -1 | -0.9804% | Not delivered | Last update august 2019: The mold production and final test required for mass production will be carried out at the same time as the funding is raised, and various certification and accessory production procedures remain. | 14 | 3 | 138 | 0 | 253.7657 | 289 | I like that Kickstarter deactivates this, yet won't refund us. Kickstarter is as much of a scam as these con-artists. Won't see me ever doing a Kickstarter again with no protections whatsoever. They lie and say the project has to deliver, but when they don't they are no consequences or refunds... What a joke...
1023 | Pixel princess | Sandbox action RPG | funded-2yrs-eveleens-oct2020 | 2018-05-25 | Funded | https://www.kickstarter.com/projects/lanzegames/pixel-princess-blitz-sandbox-roguelite-action-rpg?ref=discovery_category_newest |  | Hamburg, Germany | Germany | Games | 1347 | 8574 | 37368 | 435.8% | 2018-12-01 | 190 | Not delivered | -1 | -0.5263% | Not delivered | June 7 2020: We've been caught up in a development hell the recent few days, and I insisted that we need to a little bit more so that the footage is more polished. But due to a number of bugs which we have mostly squashed now, things took more time than I wished. | Unknown | 0 | 112 | 2 | 20
1024 | Pocketstar | Retro gaming device | funded-2yrs-eveleens-oct2020 | 2018-01-23 | Funded | https://www.kickstarter.com/projects/zepsch/pocketstar-play-retro-games-on-your-keychain?ref=discovery_category_newest | contact@zepsch.com | Ludwigsburg, Germany | Germany | Games | 471 | 28000 | 28715 | 102.6% | 2018-05-01 | 98 | 2019-05-30 | 394 | 402% | 6-24 month delay | We completed Shipping in May (Before we launched our second project). In October, we re-sent some rewards because they got lost on the way. | 3 | 5 | 107 | 3 | 50
1025 | QUBE | Wireless charger & Power bank | funded-2yrs-eveleens-oct2020 | 2021-07-11 | Funded | https://www.kickstarter.com/projects/qube/qube-powerful-dynamic-fast-charger/description | social@manu.nl | Eindhoven, Netherlands | Netherlands | Technology | 118 | 10000 | 11201 | 112% | 2019-10-01 | -649 | Not delivered | -1 | 0.1541% | Not delivered | We're terribly sorry that we are still unable to provide a set delivery timeframe. You will be informed, once more details are known. We have just received a message from our shipping partner about when QUBE will arrive in our Dutch distribution centre. Due to the busy end of the year at the airfreight and all difficulties to fly in dangerous substances (li-ion batteries), we have had extra delays. . | 3 | 2 | 78 | 0 | 130
1026 | See Sense BEAM | Bike light | funded-2yrs-eveleens-oct2020 | 2018-11-20 | Funded | https://www.kickstarter.com/projects/1670187625/see-sense-beam-and-icon2-our-brightest-bike-lights?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=818b2fa5 | team@seesense.cc | Belfast, UK | UK | Technology | 1099 | 30000 | 102255 | 340.9% | 2019-06-01 | 193 | 2021-04-01 | 670 | 347.2% | 6-24 month delay | From the comments it is clear several users have received a product. Maker claims all shipped around april 2021. Example "Got my Beam+ today! Looks good quality and very bright and compact. Gets very hot though, which may affect battery times!" | 16 | 5 | 120 | 6 | 90
1027 | Shredmate | Bike computer sensor | funded-2yrs-eveleens-oct2020 | 2017-08-29 | Funded | https://www.kickstarter.com/projects/1333727138/shredmate-tracks-mountain-bike-jumps-g-forces-and?ref=nav_search&result=project&term=Shredmate | hello@shredmate.co.uk | London, UK | UK | Technology | 203 | 11185 | 13391 | 119.7% | 2018-03-01 | 184 | 2018-05-20 | 80 | 43.48% | Delivered on time | All ShredMates were posted on Tuesday. International deliveries may not have arrived just yet, but they should be with you by the middle of next week. | 5 | 3 | 165 | 0 | 71.7672 | 60
1028 | Somnox Sleep robot | Sleep robot | funded-2yrs-eveleens-oct2020 | 2017-11-14 | Funded | https://www.kickstarter.com/projects/somnox/somnox-worlds-first-sleep-robot-to-improve-your-sl/description | support@somnoxus.zendesk.com | Delft, Netherlands | Netherlands | Design | 509 | 100000 | 200274 | 200.3% | 2018-02-01 | 79 | 2019-03-30 | 422 | 534.2% | 6-24 month delay |  | 10 | 4 | 155 | 0 | 600
1029 | SonarPen | Most affordable smart pen | funded-2yrs-eveleens-oct2020 | 2018-02-06 | Funded | https://www.kickstarter.com/projects/greenbulb/sonarpen-worlds-most-affordable-smart-pen-for-ipad | info@greenbulb.com | Hong Kong | China | Technology | 2357 | 21678 | 78490 | 362.1% | 2018-06-01 | 115 | 2018-09-27 | 118 | 102.6% | Delivered on time |  | 2 | 3 | 148 | 2 | 26.4716 | 235
1030 | The Holga printer | Mobile photography | funded-2yrs-eveleens-oct2020 | 2018-10-09 | Funded | https://www.kickstarter.com/projects/2098439381/the-holga-printer-restyling-mobile-photography?ref=phtech.go2.fund&utm_medium=referral&utm_source=phtech.go2.fund | info@holgadigital.com | Hong Kong | China | Design | 1219 | 16265 | 73017 | 448.9% | 2019-03-01 | 143 | Not delivered | -1 | -0.6993% | Not delivered | April 2019: We are sorry to announce that due to some major issues on the tooling, some parts from initial injection did not pass our quality control standards. As a result, our molds are being modified by experienced tooling technicians. | Unknown | 2 | 138 | 2 | 56.3225 | 500
1031 | UNA Grill | Portable grill | funded-2yrs-eveleens-oct2020 | 2017-06-14 | Funded | https://www.kickstarter.com/projects/922121366/una-grill-the-portable-charcoal-grill-to-carry-any/description | info@unagrill.com | Amsterdam, Netherlands | Netherlands | Design | 266 | 15000 | 32626 | 217.5% | 2017-10-01 | 109 | 2018-01-01 | 92 | 84.4% | Delivered on time | Exact delivery date not reported, comment section indicatesbackers received product in early 2018 | 5 | 1 | 114 | 0 | 150
1032 | UnoBrush | A smart toothbrush | funded-2yrs-eveleens-oct2020 | 2018-10-22 | Funded | https://www.kickstarter.com/projects/100951725/unobrush-toothbrushing-reimagined/description?ref=producthype | hello@unobrush.com | Copenhagen, Denmark | Denmark | Design | 12375 | 13457 | 972143 | 7224% | 2019-05-01 | 191 | Not delivered | -1 | -0.5236% | Not delivered | On the 10th of September 2021, the company was declared bankrupt, and Anders Hoffmann Kønigsfeldt was appointed curator. This was clearly a scam. Kickstarter was made aware it was a scam. They were allowed to raise money on other platforms for the same project with the same fraudulent claims, then once again were allowed to charge additional fees from backers in a last ditch attempt to pull every last cent from their fraud as they were being investigated by journalists in their home nation. | 3 | 3 | 130 | 0 | 190.7926 | 1420
1033 | Unravel | Fast wireless charging | funded-2yrs-eveleens-oct2020 | 2018-09-26 | Funded | https://www.kickstarter.com/projects/ampere/unravel-wireless-charging-station-travel-charger | wirelesstravel@stackpackandgo.com | New York | US | Design | 4213 | 8401 | 322349 | 3837% | 2018-12-01 | 66 | 2019-01-27 | 57 | 86.36% | Delivered on time |  | Unknown | 2 | 128 | 4 | 78.1493 | 89
1034 | UPstage 360 | First 360 smart speaker | funded-2yrs-eveleens-oct2020 | 2018-03-06 | Funded | https://www.kickstarter.com/projects/2034870069/upstage-360-the-ultimate-360-hi-res-smart-speaker?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=0b1363 | support-en@level-ten.com | Reno | US | Design | 642 | 33613 | 643078 | 1913% | 2018-07-01 | 117 | 2018-11-21 | 143 | 122.2% | Delivered on time |  | Unknown | 5 | 60 | 2 | 438.1629 | 499
1035 | Wynd | Home purifier to keep air healthy | funded-2yrs-eveleens-oct2020 | 2018-11-14 | Funded | https://www.kickstarter.com/projects/882633450/wynd-halo-home-purifier-keep-your-homes-air-health | hi@hellowynd.com | California | US | Technology | 3150 | 42030 | 721018 | 1715% | 2019-05-01 | 168 | 2020-09-08 | 496 | 295.2% | 6-24 month delay | Updates are not public, but last shipping update give on sep 8 2020 | 12 | 4 | 169 | 2 | 122.0534 | 139

## currencies
Currency | Eur conversion | Conversion date | Source
USD | 0.87808 | 2022-01-18 | https://www.xe.com
CHF | 0.95979 | 2022-01-18 | https://www.xe.com
SEK | 0.096962 | 2022-01-18 | https://www.xe.com
GBP | 1.1961 | 2022-01-18 | https://www.xe.com
HK | 0.11264 | 2022-01-18 | https://www.xe.com
DKK | 0.13436 | 2022-01-18 | https://www.xe.com

## failed-projects-reasons
Project name | Status | Link | Source text | Main stated reason for failure
Circa |  | https://www.kickstarter.com/projects/2071439898/circa-the-stand-alone-smart-alarm-that-helps-you-s?ref=discovery_category_newest | Unfortunately we ran into some problems with the current hardware and software which means that our current prototypes are not yet stable enough for usertesting. We ran into some small issues with regards to the hardware design which delayed the process of ordering prototypes and validating the hardware. While reviewing the design we found some small issues that had to be fixed before creating a new prototype.These delays also impact the production of the molds as we have to verify whether the electronics and plastics play nicely together. Last month we told you that we had difficulties with getting the display to work with the new hardware. that his toolmaker returned the assignment. He finally found another toolmaker but this came with a delay. We’re really annoyed with how this process has been handled by our manufacturer and are working to make sure that it doesn’t happen again. we had to put the project on hold due to high display prices, technology issues, and financial problems. | Hardware issues, delivery of resources issues, Financial issues
Halzae |  | https://www.kickstarter.com/projects/362994230/halzae-heroes-of-divinity-from-students-to-indiede?ref=discovery_category_newest | No news | Unknown
LeviZen |  | https://www.kickstarter.com/projects/1348567444/levizen-levitate-water-and-feel-zero-gravity?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Blog | assembly process because of its many parts. because of the complexity of LeviZen and currently we have a hold on the production | Assembly issues
MasterSous |  | https://www.kickstarter.com/projects/mastersous/mastersous-the-8-in-1-smart-cooker?ref=phtech.go2.fund&utm_medium=referral&utm_source=phtech.go2.fund | Unfortunately, the holidays slowed down our progress more than expected. The engineering team in the US and the manufacturing team in China are communicating regularly but the face to face meetings help move things along much quicker We revised the design of the base so that it is shorter in height and longer in depth. Due to an extended quality control process, This was our first Crowdfunding campaign, and we realize that we have much to learn. we have a small staff, Unfortunately, however, the outbreak of the Coronavirus has momentarily paused production, | Team experience issues Pandemic issues Hardware changes Long Quality Control
Mine kafon drone |  | https://www.kickstarter.com/projects/massoudhassani/mine-kafon-drone?ref=discovery_category | Due to a delay in the transfer of funds some of our rewards which were we are enlarging our team. One of the major draw backs was when the laser tube of our laser machine got damaged during moving Start all over again | Team problems Issues because of hardware malfunction Starter all over again because not satisfied
Mycroft Mark II |  | https://www.kickstarter.com/projects/aiforeveryone/mycroft-mark-ii-the-open-voice-assistant?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Post | Coordinating parts orders and queuing up for production across multiple companies makes it very difficult to make up time Our biggest issue to date has been the quality and reliability of the PCB Fabrication and Assembly. The challenges we’ve faced in getting the device shipped fall into three categories: Component availability. Firmware, drivers and low level software. Unfortunately our vendor hasn’t delivered. That means the screen crashes, the board overheats, and we’ve yet to see the claimed audio processing technologies working on the prototype hardware. Making complex electronics is hard. Really, really hard. Global supply chain management, uncertain development timelines, lying vendors, low quantity fabrication, quality control, firmware development, software hardware integration, intellectual property management, personnel recruitment and retention, fundraising, public relations – | Problems with the vendor Overall problems with hardawre project, didn't see them coming? Very complex project, too complex? Assembly issues
OFF GRID |  | https://www.kickstarter.com/projects/richmetson/off-grid-data-is-your-most-powerful-weapon?ref=discovery_category | In the last sprints we ran into some pretty weird and complicated to debug issues, which is why it's taken us a while to get a new build out. Our team has changed. We have realised that to get the best out of the game we have to allow space for more user testing and a bigger public beta access. There really are indie sweet spots as far as release windows go | Team changes More work than expected Bug Issues
Phoenix springs |  | https://www.kickstarter.com/projects/20171617/phoenix-springs-a-neo-noir-mystery-adventure-game?ref=discovery_category |  | Almost no communication COVID Issues
PITTA |  | https://www.kickstarter.com/projects/1627662609/pitta-transformative-autonomous-4k-selfie-drone?utm_source=ProductHype&utm_medium=Blog&utm_campaign=Post | but There is a slight delay in coordinating the schedule with the investment destinations. All these efforts and changing parts are reasons why we are experiencing delay. | Changing parts Financial problems
Pixel princess |  | https://www.kickstarter.com/projects/lanzegames/pixel-princess-blitz-sandbox-roguelite-action-rpg?ref=discovery_category_newest |  | A lot of delay by just sheer work
QUBE |  | https://www.kickstarter.com/projects/qube/qube-powerful-dynamic-fast-charger/description | all parts except the crucial part, the powerbank, are ready. difficulties to fly in dangerous substances (li-ion batteries), we have had extra delays. Unfortunately we came across technical inconsistencies with the chargers Delay in production due to Corona | Problems with shipment of products Not foreseen risks Coronavirus
See Sense BEAM |  | https://www.kickstarter.com/projects/1670187625/see-sense-beam-and-icon2-our-brightest-bike-lights?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=818b2fa5 | there was a delay in the supply chain has required more iterations than originally expected t In testing, we found that the Bluetooth antenna wasn’t performing quite as well as we would have liked | Hardware issues Supply chain issues Has required more time then they originally thought
The Holga printer |  | https://www.kickstarter.com/projects/2098439381/the-holga-printer-restyling-mobile-photography?ref=phtech.go2.fund&utm_medium=referral&utm_source=phtech.go2.fund | some major issues on the tooling, some parts from initial injection did not pass our quality control standards. | Hardware issues Didn't know where they got into
UnoBrush |  | https://www.kickstarter.com/projects/100951725/unobrush-toothbrushing-reimagined/description?ref=producthype | high number of backers, has meant that the two manufacturers scheduled to produce the UNOBRUSH, unfortunately, were not able to meet such levels of demand. When we launched the campaign last fall, we didn’t know which direction the project would take. Our analysis showed that the project would be delayed significantly in addition to being quite costly. Also, our technical team could not guarantee that it would work as intended, and we would, therefore, be risking further delay. | Team had no idea what they got into Way too many backers and orders Supply chain problem
Alhambra Designer's edition |  | https://www.kickstarter.com/projects/1082720051/alhambra-designers-edition?ref=discovery_category_newest | We are going to increase the thickness of the plastic by 25% to make sure it is sturdy. This, however, will cause a delay in production, and at the moment we would like to wait for this so that all of the artwork has a consistent style throughout the game. We had a logistical problem preparing the games to ship that delayed the process by two weeks | Changing parts Employer sick Logistical Problems
Bee scanning |  | https://www.kickstarter.com/projects/1418874888/beescanning?ref=discovery_staff_picks_category | Nothing
GOSPACE |  | https://www.kickstarter.com/projects/722274067/gospace-expandable-5g-wireless-storage-and-streami | Due to an operational error on Backerkit, we have incorrectly marked all pledges as "shipped" | Logistical error at supplier
HEY |  | https://www.kickstarter.com/projects/1596731227/hey-a-revolutionary-bracelet-that-sends-touch-over?ref=discovery_category | However, we discovered that after repetitive use, some bracelets showed issues with the battery and motor. Therefore, we had to make the difficult decision of repealing the shipping order nfortunately, one of the parts – the PCB that establishes the Bluetooth connection – didn’t meet the requirements for certification. The bad news is that we cannot manufacture all the bracelets at once, which means shipping is going to take place in batches | Hardware problems Supply chain problem
LeveTop |  | https://www.kickstarter.com/projects/1727015699/levetop-the-autonomous-folding-drone | t will take us some time to make precise adjustment. To make sure that everyone could own a drone with the best shooting performance , our team decides to delay our delivery time until the end of the August. | Hardware issues
Mayu |  | https://www.kickstarter.com/projects/mayuwater/mayu-keep-your-water-healthy-with-a-natural-swirli?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=c23c0c8e | and miscalculated the time it takes for some critical steps. or us, this is the first time going into mass production, an amazing, challenging and sometimes frustrating realm. | Hardware issues Unexperienced team Corona virus Supply chain problems
Pocketstar |  | https://www.kickstarter.com/projects/zepsch/pocketstar-play-retro-games-on-your-keychain?ref=discovery_category_newest | will be delayed because we received your pledges almost a month later than expected. But unfortunately, we are still waiting for some components. | Delay in pledges, third party Changes in hardware Supply chain delay And since we did not have such a certificate, they had to be sent back.
Somnox Sleep robot |  | https://www.kickstarter.com/projects/somnox/somnox-worlds-first-sleep-robot-to-improve-your-sl/description | we encountered an unexpected problem with the materials selected, which results in a reselection of some critical materials | Supply chain delivery
Wynd |  | https://www.kickstarter.com/projects/882633450/wynd-halo-home-purifier-keep-your-homes-air-health?utm_source=kickbooster-direct&utm_medium=kickbooster&utm_content=link&utm_campaign=9fd1fe87 | On the Wynd Halo, we had to make many engineering changes which we think will result in a more accurate, better looking, and better performing device. | Hardware changes Supply chain delays Corona virus
Zano |  | https://www.kickstarter.com/projects/torquing/zano-autonomous-intelligent-swarming-nano-drone | "An unfortunate combination of overblown confidence and underwhelming skill" (Techniwant) Note that Kickstarter did an investigation: https://medium.com/kickstarter/how-zano-raised-millions-on-kickstarter-and-left-backers-with-nearly-nothing-85c0abe4a6cb | Lack of skills, stretch goals
Coolest cooler |  | https://www.kickstarter.com/projects/ryangrepper/coolest-cooler-21st-century-cooler-thats-actually
Epiphany onE puck |  | https://www.kickstarter.com/projects/epiphanylabs/epiphany-one-puck/comments
|  |  | Product changes/problems | Supply chain issues | Third party problems | Covid-19 | Financial problems | Team experience
Circa |  |  | 1 | 1 |  |  | 1
Halzae
LeviZen |  |  |  | 1
MasterSous |  |  | 1 | 1 |  | 1 |  | 1
Mine kafon drone |  |  | 1 |  |  |  |  | 1
Mycroft Mark II |  |  |  | 1 | 1 |  |  | 1
OFF GRID | [7 empty] | 1
Phoenix springs | [5 empty] | 1
PITTA |  |  | 1 |  |  |  | 1
Pixel princess |  |  | 1 | 1
QUBE |  |  | 1 | 1 | 1 | 1
See Sense BEAM |  |  | 1 | 1
The Holga printer |  |  | 1 |  |  |  |  | 1
UnoBrush |  |  | 1 | 1 |  |  |  | 1
Alhambra Designer's edition |  |  | 1 | 1
Bee scanning
GOSPACE |  |  |  |  | 1
HEY |  |  | 1 | 1
LeveTop |  |  | 1
Mayu |  |  | 1 | 1 |  | 1 |  | 1
Pocketstar |  |  | 1 | 1 |  |  | 1
Somnox Sleep robot |  |  |  | 1
Wynd |  |  | 1 | 1 |  | 1
|  |  | 15 | 14 | 3 | 5 | 3 | 7
|  |  |  | Reason | Count
|  |  |  | Product changes/problems | 15
|  |  |  | Supply chain issues | 14
|  |  |  | Team experience | 7
|  |  |  | Covid-19 | 5
|  |  |  | Third party problems | 3
|  |  |  | Financial problems | 3